## Sheet1
PROJECT BACKLOG
#REF! | = highest Reference ID number
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
2 | 1 | 1 | user story | 订单信息查询 | 作为一个用户，我想看查看我的订单。 | Initial Feature | Not Done | 3 | 95 |  | 3
6 | 1 | 1 | user story | 权限分配 | 作为一个管理者，我想给用户分配权限。 | Initial Feature | Not Done | 2 | 95 |  | 2
5 | 1 | 1 | user story | 活动演出票 | 作为一个用户，我想买到演出，活动的票。 | Initial Feature | Not Done | 2 | 94 |  | 1
7 | 1 | 1 | user story | 注册 | 作为一个用户，我想有登录的资格。 | Initial Feature | Not Done | 1 | 92 |  | 1
11 | 1 | 1 | user story | 退出 | 作为一个用户，我希望不用时，可以直接退出。 | Initial Feature | Not Done | 2 | 90 |  | 2
1 | 1 | 1 | user story | QQ登录 | 作为一个用户，我希望能够通过QQ登录，以便于更快捷的登录系统，而省去注册环节。 | Initial Feature | Not Done | 3 | 88 |  | 2
4 | 1 | 1 | user story | 艺术品购买 | 作为一个观众，我希望能购买演出后的艺术品。 | Initial Feature | Not Done | 2 | 88 |  | 2
3 | 1 | 1 | user story | 用户信息查询 | 作为一个管理员，我想查看用户的信息。 | Initial Feature | Not Done | 2 | 85 |  | 1
8 | 1 | 1 | user story | 搜索 | 作为一个用户，我想直接找到我想要的活动，演出详情。 | Initial Feature | Not Done | 2 | 82 |  | 2
9 | 1 | 1 | user story | 热门推荐 | 作为一个用户，我想给我推荐大卖的活动或演出。 | Initial Feature | Not Done | 2 | 82 |  | 2
10 | 1 | 1 | user story | 关注 | 作为一个用户，我希望能被别的用户关注增长自己的热度。 | Initial Feature | Not Done | 1 | 70 |  | 1
Total |  | 11 | [5 empty] | 22 |  |  | 19
Generate index cards
Note on A4: Luc Segers: This is the highest reference ID number used so far.
Note on A5: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B5: Luc Segers: This is the release where the story will be developped
Note on C5: Luc Segers: This is the sprint where the story will be developped
Note on D5: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F5: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G5: Luc Segers: Type of the story.
Note on H5: Luc Segers: Status of the story
Note on I5: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J5: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on K5: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on L5: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on M5: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on N5: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on O5: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information
Note on C17: Luc Segers: Total amount of stories available in the project backlog
Note on I17: Luc Segers: total amount of estimated hours